## Agile Product Backlog
AGILE PRODUCT BACKLOG
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
|  | Sprint 1 | A.Santella - C.Salsano - C.Tedesco - A.Zuozo |  |  |  | Yes | High | Complete | 26
1 | User Management |  | A.Santella | 2020-11-21 | 2020-12-01 | Yes | Yes | High | Complete | 3 | Yes | This section is for the drop-down list
2 | Competences Management |  | C.Salsano | 2020-11-21 | 2020-12-01 | Yes | Yes | High | Complete | 3 | Yes | Yes | High | Complete
6 | Sites Management |  | A.Zuozo | 2020-11-21 | 2020-12-01 | Yes | Yes | High | Complete | 3 | Yes
9 | Maintenance typologies Management |  | C.Tedesco | 2020-11-21 | 2020-12-01 | Yes | Yes | High | Complete | 3 | Yes
8 | Maintenance Procedure Management |  | A.Santella - C.Salsano - C.Tedesco - A.Zuozo | 2020-11-29 | 2020-12-03 | Yes | Yes | Medium | Complete | 5 | Yes
|  | Sprint 2 | A.Santella - C.Salsano - C.Tedesco - A.Zuozo |  |  |  | Yes | Medium | Complete | 15 |  |  | Low | Not Started
3 | Assign Maintainer competences |  | C.Tedesco | 2020-12-07 | 2020-12-09 | Yes | Yes | Medium | Complete | 1 | Yes
4 | Worknotes Management |  | A.Zuozo | 2020-12-11 | 2020-12-14 | Yes | Yes | Low | Complete | 3 | Yes
5 | Accesses Management |  | C.Tedesco |  |  | Yes | Yes | Low | Not Started | 5 | Yes
7 | Materials Management |  | C.Salsano | 2020-12-04 | 2020-12-05 | Yes | Yes | Medium | Complete | 3 | Yes
10 | Maintenance activities Management |  | A.Santella - C.Salsano | 2020-12-05 | 2020-12-11 | Yes | Yes | High | Complete | 8 | Yes
11 | EWO Management |  | A.Zuozo | 2020-12-11 | 2020-12-14 | Yes | Yes | High | Complete | 3 | Yes
12 | Assigned tickets visualization |  | C.Tedesco | 2020-12-11 | 2020-12-15 | Yes | Yes | High | Complete | 1 | Yes