## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
User Story #1 | 3 | A.Santella | Done
Development of the related backend part |  | " " | Done | 3 | DAY 1: 2; DAY 2: 1
Visualize system users |  | " " | Done | 8 | DAY 2: 1; DAY 3: 1.5; DAY 4: 2; DAY 5: 2; DAY 6: 0.5
Create system users |  | " " | Done | 3.5 | DAY 6: 1; DAY 7: 0.5
Modify/Delete system users |  | " " | Done | 2.5 | DAY 7: 3; DAY 8: 2
Testing |  | " " | Done | 1 | bar: DAY 8
User Story #2 | 3 | C.Salsano | Done
Development of the related backend part |  | " " | Done | 3 | DAY 1: 2; DAY 2: 1
Visualize list of competences |  | " " | Done | 8 | DAY 2: 0.5; DAY 3: 2; DAY 4: 0.5
Create list of competences |  | " " | Done | 3.5 | DAY 4: 0.5; DAY 5: 2; DAY 6: 2
Modify/Delete list of competences |  | " " | Done | 2.5 | DAY 7: 3
Testing |  | " " | Done | 1 | bar: DAY 7
User Story #6 | 3 | A.Zuozo | Done
Development of the related backend part |  | " " | Done | 3 | DAY 1: 2; DAY 2: 1
Visualize sites |  | " " | Done | 8 | DAY 2: 1; DAY 3: 2; DAY 4: 2; DAY 5: 3
Create sites |  | " " | Done | 3.5 | DAY 5: 1; DAY 6: 3; DAY 7: 0.5
Modify/Delete sites |  | " " | Done | 2.5 | DAY 7: 3
Testing |  | " " | Done | 1 | bar: DAY 7
User Story #9 | 3 | C.Tedesco | Done
Development of the related backend part |  | " " | Done | 3 | DAY 1: 2; DAY 2: 1
Visualize typologies |  | " " | Done | 8 | DAY 2: 0.5; DAY 3: 3; DAY 4: 3; DAY 5: 1.5
Create typologies |  | " " | Done | 3.5 | DAY 5: 1.5; DAY 6: 2
Modify/Delete typologies |  | " " | Done | 2.5 | DAY 7: 1; DAY 8: 3
Testing |  | " " | Done | 1 | bar: DAY 8
User Story #8 | 5 | A.Zuozo, A.Santella, C.Salsano, C.Tedesco | Done
Development of the related backend part |  | C.Tedesco | Done | 3 | DAY 1: 2; DAY 2: 1
Visualize procedures |  | C.Salsano | Done | 8 | DAY 8: 3; DAY 9: 2; DAY 10: 2
Create procedures |  | A.Zuozo | Done | 3.5 | DAY 8: 2; DAY 9: 1
Modify/delete procedures |  | A.Santella | Done | 2.5 | DAY 9: 3
Assign list of competences to procedures |  | C.Tedesco | Done | 2 | DAY 10: 2
Testing |  | " " | Done | 1 | bar: DAY 10
TOTAL |  |  |  | 92 | 10 | 8 | 8.5 | 8 | 11 | 8.5 | 13 | 12 | 6 | 5
ESTIMATED EFFORT |  |  |  | 92 | 82 | 74 | 65.5 | 57.5 | 46.5 | 38 | 25 | 13 | 7 | 0
ESTIMATED EFFORT |  |  |  | 92 | 82.8 | 73.6 | 64.4 | 55.2 | 46 | 36.8 | 27.6 | 18.4 | 9.2 | 0