## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
User Story #3 | 1 | C.Tedesco | Done
Development of the related backend part |  | " " | Done | 3 | DAY 3: 2; DAY 4: 2
Associate competences to maintainer |  | " " | Done | 3 | DAY 3: 2; DAY 4: 2
Testing |  |  | Done | 1 | bar: DAY 4
User Story #4 | 3 | A.Zuozo | Done
Development of the related backend part |  | " " | Done | 3 | DAY 6: 3
Visualize notes |  | " " | Done | 5 | DAY 6: 1; DAY 7: 2
Create notes |  | " " | Done | 3.5 | DAY 6: 1; DAY 7: 2
Modify/delete notes |  | " " | Done | 2.5 | bar: DAY 7
Testing |  |  | Done | 1 | bar: DAY 8
User Story #5 | 5 | C.Tedesco
Development of the related backend part |  | " " |  | 3
Implement a mechanism to record accesses |  | " " |  | 10
User Story #7 | 3 | C.Salsano | Done
Development of the related backend part |  | " " | Done | 3 | DAY 1: 2
Visualize materials |  | " " | Done | 5 | DAY 1: 1; DAY 2: 3
Create materials |  | " " | Done | 3 | bar: DAY 1 to DAY 2
Delete materials |  | " " | Done | 2 | bar: DAY 1 to DAY 2
Testing |  |  | Done | bar: DAY 3
User Story #10 | 8 | A.Santella - C.Salsano | Done
Development of the related backend part |  | " " | Done | 3 | DAY 2: 3; DAY 3: 2
Visualize maintenance activities |  | " " | Done | 5 | DAY 2: 2; DAY 3: 0.5; DAY 5: 3
Create maintenance activities |  | " " | Done | 3.5 | DAY 5: 2
Modify/Delete maintenance activities |  | " " | Done | 2.5 | DAY 5: 2
Select maintenance activities |  | " " | Done | 2 | DAY 2: 1.5; DAY 3: 1; DAY 4: 2
Assign maintenance activies |  | " " | Done | 4 | DAY 4: 1; DAY 5: 2; DAY 6: 1
Testing |  |  | Done | bar: DAY 6
User Story #11 | 3 | A.Santella - C.Tedesco | Done
Development of the related backend part |  | " " | Done | 3 | DAY 6: 3
Visualize EWO compilation screen |  | " " | Done | 5 | DAY 6: 2; DAY 7: 2
Select EWO |  | " " | Done | 3.5 | DAY 6: 1; DAY 7: 2; DAY 8: 1
Assign EWO |  | " " | Done | 2.5 | DAY 8: 3
Testing |  |  | Done | bar: DAY 8
User Story #12 | 1 | A.Zuozo | Done
Development of the related backend part |  | " " | Done | 3 | DAY 6: 3
Visualize assigned tickets' state |  | " " | Done | 2 | DAY 9: 3
Testing |  |  | Done | bar: DAY 9
TOTAL |  |  |  | 87 | 5 | 11.5 | 8.5 | 8 | 9 | 16 | 9 | 6 | 4 | 0
ESTIMATED EFFORT |  |  |  | 87 | 82 | 70.5 | 62 | 54 | 45 | 29 | 20 | 14 | 10 | 10
ESTIMATED EFFORT |  |  |  | 87 | 78.3 | 69.6 | 60.9 | 52.2 | 43.5 | 34.8 | 26.1 | 17.4 | 8.7 | 0